## 📋 Executive Summary
XLRI Course-Bidding Platform — Project Cost Estimate
Executive Summary ¦ Prepared: March 2026 ¦ Version 1.0
XLRI – Xavier School of Management ¦ Confidential & For Internal Use
PROJECT OVERVIEW
Project Name | XLRI Course-Bidding & Selection Platform
Platform Type | Full-Stack Web Application (Next.js + PostgreSQL)
Tech Stack | Next.js 16, React 19, Prisma ORM, PostgreSQL, TailwindCSS, NextAuth
Target Users | Students (BM/HRM), Professors, Administrators
Development Status | MVP Completed — Ready for Review
COST SUMMARY
Category | Cost (₹) | Details
Phase 1 — Discovery & Design | ₹ 80,000 | UI/UX, wireframes, DB design
Phase 2 — Core Development | ₹ 3,60,000 | Backend, frontend, auth, bidding engine
Phase 3 — Testing & QA | ₹ 60,000 | Unit, integration, UAT
Phase 4 — Deployment & DevOps | ₹ 40,000 | Cloud setup, CI/CD, domain, SSL
Phase 5 — Training & Handover | ₹ 20,000 | Admin training, documentation
One-Time Total | ₹ 5,60,000 | All dev phases combined
Annual Infrastructure (Hosting) | ₹ 84,000 | Cloud server + DB + backup + CDN
Annual Maintenance & Support | ₹ 96,000 | Bug fixes, updates, monitoring
Annual Recurring Total | ₹ 1,80,000 | Year 1 post-launch
GRAND TOTAL (Year 1) | ₹ 7,40,000 | Development + Infra + Support
TIMELINE SUMMARY
Total Development Duration | 14–16 Weeks | ~4 months
Go-Live Target | July 2026 | Before new academic year
Post-Launch Support | 12 Months | Included in AMC

## 💻 Development Cost
Development Cost Breakdown
Detailed Phase-wise Engineering Effort & Fees
XLRI – Xavier School of Management ¦ Confidential & For Internal Use
Module / Task | Role | Hours | Rate (₹/hr) | Amount (₹) | Notes
PHASE 1 — DISCOVERY & DESIGN (2 weeks)
Requirements gathering & stakeholder interviews | Business Analyst | 16 | 600 | 9600 | Scope finalization
Database schema & ER diagram design | Lead Developer | 10 | 900 | 9000 | 20 models, relations, enums
UI/UX wireframes (Figma) — 15 screens | UI/UX Designer | 24 | 700 | 16800 | All portals: Admin/Prof/Student
System architecture design | Solution Architect | 8 | 1000 | 8000 | Tech stack decisions
Phase 1 Sub-Total |  | 58 |  | 43400
PHASE 2 — CORE DEVELOPMENT (8 weeks)
NextAuth setup (JWT, credentials, session) | Lead Developer | 12 | 900 | 10800 | Role-based: Admin/Prof/Student
User management & role permissions | Lead Developer | 16 | 900 | 14400 | CRUD + access control
Prisma schema + migrations + seed data | Backend Developer | 20 | 800 | 16000 | Full DB setup + 20 models
REST/Server-Action API — Courses module | Backend Developer | 24 | 800 | 19200 | CRUD + attachments
REST/Server-Action API — Bidding engine | Backend Developer | 40 | 900 | 36000 | Core bidding logic
REST/Server-Action API — Allocation engine | Backend Developer | 36 | 900 | 32400 | Tie-break, waitlist, quota
REST/Server-Action API — Notifications | Backend Developer | 16 | 800 | 12800 | In-app notifications
Audit log & import jobs module | Backend Developer | 12 | 800 | 9600 | Full audit trail
Admin portal — Dashboard + Cycles management | Frontend Developer | 28 | 750 | 21000 | Bidding cycle CRUD
Admin portal — Course & offering management | Frontend Developer | 24 | 750 | 18000 | Seat caps, tie-break
Admin portal — Allocation results & reports | Frontend Developer | 20 | 750 | 15000 | Charts via Recharts
Admin portal — Audit log viewer | Frontend Developer | 12 | 750 | 9000 | Filterable log table
Professor portal — Course creation & upload | Frontend Developer | 20 | 750 | 15000 | Outline PDF upload
Student portal — Bidding interface | Frontend Developer | 32 | 750 | 24000 | Live point tracker
Student portal — Allocation & confirmation | Frontend Developer | 16 | 750 | 12000 | CONFIRM / WITHDRAW
Public website (Home, About, FAQ, Blog) | Frontend Developer | 20 | 650 | 13000 | Marketing pages
Responsive design (mobile/tablet) | Frontend Developer | 16 | 700 | 11200 | TailwindCSS breakpoints
Phase 2 Sub-Total |  | 364 |  | 289400
PHASE 3 — TESTING & QA (2 weeks)
Unit tests (Vitest) — API & business logic | QA / Developer | 20 | 700 | 14000 | Target >80% coverage
Integration tests — End-to-end bidding flow | QA Engineer | 16 | 650 | 10400 | Full round lifecycle
User Acceptance Testing (UAT) | QA + Stakeholders | 16 | 600 | 9600 | Admin + student scenarios
Performance & load testing | QA Engineer | 8 | 650 | 5200 | Simulate 500 concurrent users
Security review (OWASP basics) | Lead Developer | 8 | 900 | 7200 | Auth, SQL injection, XSS
Phase 3 Sub-Total |  | 68 |  | 46400
PHASE 4 — DEPLOYMENT & DEVOPS (1 week)
Cloud server setup (AWS/GCP/Railway) | DevOps Engineer | 8 | 850 | 6800 | Production environment
PostgreSQL setup + automated backups | DevOps Engineer | 6 | 850 | 5100 | Daily snapshots
CI/CD pipeline (GitHub Actions) | DevOps Engineer | 8 | 850 | 6800 | Auto deploy on merge
Domain, SSL certificate, DNS config | DevOps Engineer | 4 | 700 | 2800 | HTTPS enforced
Environment variables & secrets management | DevOps Engineer | 4 | 700 | 2800 | Prod vs staging config
Phase 4 Sub-Total |  | 30 |  | 24300
PHASE 5 — TRAINING & HANDOVER (1 week)
Admin user training (2 sessions × 2 hrs) | Lead Developer | 8 | 900 | 7200 | Live + recorded
Technical documentation & user manual | Technical Writer | 16 | 500 | 8000 | PDF + wiki
Source code handover + git repo setup | Lead Developer | 4 | 900 | 3600 | Private repo + README
Phase 5 Sub-Total |  | 28 |  | 18800
TOTAL DEVELOPMENT COST (ALL PHASES) |  |  |  | 422300 | One-time fee

## 🌐 Infrastructure
Infrastructure & Hosting Cost
Annual recurring costs for cloud, database, CDN, email & monitoring
XLRI – Xavier School of Management ¦ Confidential & For Internal Use
Service / Component | Provider (Suggested) | Monthly (₹) | Annual (₹) | Tier/Plan | Notes
COMPUTE & HOSTING
App Server (Next.js + Node.js) | Railway / Render / AWS EC2 | 2500 | 30000 | Starter/Hobby Pro | 2 vCPU, 4 GB RAM
PostgreSQL Managed Database | Supabase / Railway / RDS | 1500 | 18000 | Pro tier | 10 GB storage, daily backups
Static Asset CDN | Cloudflare Free / AWS S3 | 300 | 3600 | Free–Pay-as-go | Course PDFs, images
COMPUTE Sub-Total |  | 4300 | 51600
COMMUNICATION & EMAIL
Transactional Email | Resend / SendGrid | 400 | 4800 | Up to 10k emails/mo | Notifications, OTP
COMMUNICATION Sub-Total |  | 400 | 4800
SECURITY & MONITORING
SSL Certificate | Let's Encrypt (Free) | 0 | 0 | Free | Auto-renew via Certbot
DDoS Protection & WAF | Cloudflare Free Plan | 0 | 0 | Free | Basic protection
Application Monitoring | Sentry.io | 500 | 6000 | Developer plan | Error tracking, alerts
Uptime Monitoring | BetterUptime / UptimeRobot | 200 | 2400 | Free–Starter | 5-min checks, SMS alerts
SECURITY Sub-Total |  | 700 | 8400
BACKUP & DR
Automated DB Backups (offsite) | AWS S3 / Backblaze B2 | 300 | 3600 | Pay-as-go | 30-day retention
BACKUP Sub-Total |  | 300 | 3600
DOMAIN & DNS
Domain Name (.ac.in / .in) | GoDaddy / NIXI | 0 | 1500 | Annual renewal | Owned by XLRI
DOMAIN Sub-Total |  | 0 | 1500
TOTAL ANNUAL INFRASTRUCTURE COST |  | 5700 | 69900 |  | Per year

## 🔧 Maintenance (AMC)
Annual Maintenance Contract (AMC)
Post-launch support, updates, and SLA terms
XLRI – Xavier School of Management ¦ Confidential & For Internal Use
Service | Frequency | Hours/Year | Cost (₹) | Description
Bug fixes & production incidents | On-demand | 24 | 21600 | Priority-1 fix within 24 hrs, P2 within 72 hrs
Security patches & dependency updates | Monthly | 12 | 9600 | npm updates, vuln scans, CVE patches
Feature enhancements (minor) | Quarterly | 20 | 16000 | Up to 20 hrs/year of new small features
Database optimization & index tuning | Bi-annual | 8 | 7200 | Query profiling + index review
Backup verification & DR drill | Quarterly | 4 | 3600 | Restore test from backup
Performance monitoring & reporting | Monthly | 6 | 4800 | Monthly health report to admin
User support (email/ticketing) | On-demand | 24 | 14400 | Admin & faculty query resolution
Annual audit log review & cleanup | Annual | 4 | 3600 | Archival of old audit records
Documentation updates | As needed | 8 | 4000 | Reflects new features/changes
TOTAL ANNUAL AMC COST |  | 110 | 84800 | Billed annually
SLA TERMS — SERVICE LEVEL AGREEMENT
Priority Level | Response Time | Resolution Time | Examples
P1 — Critical | 2 hours | 24 hours | App down, login broken, data loss
P2 — High | 8 hours | 72 hours | Major feature broken, allocation wrong
P3 — Medium | 24 hours | 5 business days | Minor bug, UI issue
P4 — Low | 72 hours | 10 business days | Enhancement, cosmetic

## 📅 Project Timeline
Project Timeline — Gantt Overview
14–16 Week Delivery Plan ¦ Start: April 2026 ¦ Go-Live: July 2026
XLRI – Xavier School of Management ¦ Confidential & For Internal Use
Phase / Task | Start Wk | End Wk | Start Date | End Date | Deliverables | Owner
PHASE 1 — Discovery & Design | Wk 1 | Wk 2 | 07 Apr 2026 | 14 Apr 2026 | Wireframes, DB Schema, Architecture Doc | BA + Architect
Requirements Gathering | Wk 1 | Wk 1 | 07 Apr 2026 | 07 Apr 2026 | BRD document signed off | Business Analyst
UI/UX Wireframes | Wk 1 | Wk 2 | 07 Apr 2026 | 14 Apr 2026 | Figma prototypes (15 screens) | UI/UX Designer
DB Design & Architecture | Wk 2 | Wk 2 | 14 Apr 2026 | 14 Apr 2026 | ER diagram, tech stack confirmed | Lead Developer
PHASE 2 — Core Development | Wk 3 | Wk 10 | 21 Apr 2026 | 09 Jun 2026 | Working application (all modules) | Dev Team
Auth & User Management | Wk 3 | Wk 3 | 21 Apr 2026 | 21 Apr 2026 | Login, roles, sessions | Lead Dev
Database & Seed Data | Wk 3 | Wk 4 | 21 Apr 2026 | 28 Apr 2026 | Migrations, test data | Backend Dev
Bidding Engine API | Wk 4 | Wk 7 | 28 Apr 2026 | 19 May 2026 | Bidding, allocation, tie-break | Backend Dev
Admin Portal | Wk 5 | Wk 8 | 05 May 2026 | 26 May 2026 | Full admin CRUD + reports | Frontend Dev
Professor Portal | Wk 6 | Wk 8 | 12 May 2026 | 26 May 2026 | Course + offering mgmt | Frontend Dev
Student Portal | Wk 7 | Wk 9 | 19 May 2026 | 02 Jun 2026 | Bidding UI + results | Frontend Dev
Notifications & Audit | Wk 8 | Wk 10 | 26 May 2026 | 09 Jun 2026 | In-app alerts, audit trail | Backend Dev
Public Website | Wk 9 | Wk 10 | 02 Jun 2026 | 09 Jun 2026 | Home, About, FAQ pages | Frontend Dev
PHASE 3 — Testing & QA | Wk 11 | Wk 12 | 16 Jun 2026 | 23 Jun 2026 | Test reports, UAT sign-off | QA Team
Unit & Integration Tests | Wk 11 | Wk 11 | 16 Jun 2026 | 16 Jun 2026 | 80%+ Vitest coverage | Dev + QA
User Acceptance Testing | Wk 11 | Wk 12 | 16 Jun 2026 | 23 Jun 2026 | Stakeholder sign-off | QA + Admin
Performance & Security | Wk 12 | Wk 12 | 23 Jun 2026 | 23 Jun 2026 | Load test report, OWASP check | QA Engineer
PHASE 4 — Deployment | Wk 13 | Wk 13 | 30 Jun 2026 | 30 Jun 2026 | Live URL, CI/CD pipeline, SSL | DevOps
Cloud Setup | Wk 13 | Wk 13 | 30 Jun 2026 | 30 Jun 2026 | Prod server + DB configured | DevOps
CI/CD Pipeline | Wk 13 | Wk 13 | 30 Jun 2026 | 30 Jun 2026 | GitHub Actions workflow | DevOps
Go-Live (Staging → Prod) | Wk 13 | Wk 13 | 30 Jun 2026 | 30 Jun 2026 | Production URL live | DevOps + Lead Dev
PHASE 5 — Training & Handover | Wk 14 | Wk 15 | 07 Jul 2026 | 14 Jul 2026 | Trained admins, full documentation | Lead Dev
Admin Training Sessions | Wk 14 | Wk 14 | 07 Jul 2026 | 07 Jul 2026 | 2 × 2-hour sessions | Lead Dev
Documentation & Handover | Wk 14 | Wk 15 | 07 Jul 2026 | 14 Jul 2026 | User manual, code repo, README | Tech Writer
POST-LAUNCH SUPPORT | Wk 16 | Wk 15 | 21 Jul 2026 | Ongoing | AMC begins (12 months) | Support Team
Note: Dates are indicative. Final schedule subject to project kickoff confirmation.

## 💰 Total Cost Summary
Total Cost Summary
All-In Cost: Development + Infrastructure + Support
XLRI – Xavier School of Management ¦ Confidential & For Internal Use
Cost Category | Amount (₹) | Billing | Remarks
ONE-TIME COSTS
Phase 1 — Discovery & Design | 80000 | One-time | Paid at kickoff (50%) + milestone
Phase 2 — Core Development | 360000 | One-time | Milestone-based: 30-40-30
Phase 3 — Testing & QA | 60000 | One-time | On UAT completion
Phase 4 — Deployment & DevOps | 40000 | One-time | On go-live
Phase 5 — Training & Handover | 20000 | One-time | On final handover
Total Development (One-Time) | 560000 | One-time
ANNUAL RECURRING COSTS (Year 1)
Infrastructure & Hosting | 69600 | Annual | Cloud + DB + CDN + Email + Monitoring
Domain Renewal | 1500 | Annual | .ac.in domain
Annual Maintenance Contract | 96000 | Annual | Bug fixes, updates, support (AMC)
Total Annual Recurring | 167100 | Annual
GRAND TOTAL — YEAR 1 | 727100 | One-time + Annual | Dev + Infra + AMC
YEAR 2 ONWARDS (per year) | 167100 | Annual | Infra + AMC only
SUGGESTED PAYMENT SCHEDULE
Milestone | % of Dev Cost | Amount (₹) | When
Advance / Kickoff | 30% | 168000 | On project sign-off
Phase 1 + Phase 2 Mid | 40% | 224000 | End of Week 6 (mid-development)
Phase 3 + 4 + 5 (Go-Live) | 30% | 168000 | On production go-live + UAT sign-off
Total Development Fee | 100% | 560000
Infrastructure — Year 1 | — | 69600 | Annual, paid upfront
AMC — Year 1 | — | 96000 | Annual, post go-live

## 📝 Assumptions & T&C
Assumptions, Scope & Terms and Conditions
Please read carefully before approving the cost sheet
XLRI – Xavier School of Management ¦ Confidential & For Internal Use
SCOPE INCLUSIONS
1. | Full-stack web application (Next.js 16 + PostgreSQL) as scoped
2. | Three portals: Admin, Professor, Student
3. | Course bidding engine with multi-round support, tie-breaking, waitlist, quota rules
4. | Notification system (in-app), Audit log, Import jobs module
5. | Responsive design (desktop + tablet + mobile)
6. | Authentication via NextAuth (credentials-based, role-based access control)
7. | One round of UAT revisions (up to 10 change requests)
8. | Source code ownership transferred to XLRI on final payment
9. | 12-month AMC (if contracted separately)
SCOPE EXCLUSIONS
1. | Mobile native apps (iOS / Android) — web-only
2. | LDAP / Active Directory / SSO integration (priced separately if needed)
3. | ERP or Banner / SAP integration (separate project)
4. | Custom email design / branding beyond basic templates
5. | Data migration from existing legacy system (quoted separately)
6. | Any hardware procurement
ASSUMPTIONS
1. | XLRI will provide domain credentials and a technical contact within 1 week of kickoff
2. | Stakeholder feedback turnaround time: ≤ 5 business days per review cycle
3. | Content (course descriptions, FAQs, policy text) provided by XLRI
4. | Cloud hosting environment to be decided jointly at kickoff
5. | Requirements are frozen after Phase 1 sign-off; changes thereafter attract change requests
6. | Rates are in Indian Rupees (INR); inclusive of developer fees, not inclusive of GST
COMMERCIAL TERMS
1. | GST @ 18% applicable on all invoices (not included in above figures)
2. | Prices valid for 60 days from date of this document (March 2026)
3. | Change requests beyond agreed scope: ₹800/hour (estimated and approved before start)
4. | Cancellation after kickoff: 30% of total project cost non-refundable
5. | Intellectual property transferred to XLRI upon receipt of final payment
6. | Penalty clause: delay beyond agreed milestones due to developer side — 0.5% per week
CONTACT / VENDOR DETAILS
1. | Prepared by: [Developer Name / Agency Name]
2. | Contact Email: [email@example.com]
3. | Phone: [+91-XXXXXXXXXX]
4. | Date: 17 March 2026
5. | Quote Reference: XLRI-2026-001